# Broadway & Festival Volumetric Capture Strategy - Premium Gaussian Splatting Approach

## Executive Summary

Capturing Broadway shows and large-scale festivals with premium Gaussian Splatting quality represents the pinnacle of volumetric video production. This document outlines realistic paths to achieving cinema-quality 6DOF capture of theatrical performances and live events, from full-scale professional deployments to emerging hybrid approaches.

Key Finding: Full Broadway-scale volumetric capture requires $500K-2M initial investment for professional systems, but hybrid approaches ($150K-400K) can deliver comparable quality for key moments while maintaining practical workflows and budgets.

Critical Insight: The technology exists TODAY (November 2025) to achieve this. The challenges are operational, not technical.

## Table of Contents

- The Scale Challenge

- Broadway Theater Requirements

- Festival Requirements

- Full Premium Approach

- Hybrid Approach (Recommended)

- Emerging Technology Path

- Operational Considerations

- Case Studies & Precedents

- Detailed Cost Analysis

- 3-Year Roadmap

- ROI & Business Model

- Technical Implementation Guide

## The Scale Challenge

### Broadway Theater Dimensions

Typical Broadway Stage: - Width: 40-60 feet (12-18 meters) - Depth: 30-50 feet (9-15 meters) - Height: 20-40 feet (6-12 meters) to grid - Proscenium arch: 30-40 feet wide - Capture volume: ~18,000-54,000 cubic feet

Performance Characteristics: - Performers: 1-30+ on stage simultaneously - Movement range: Full stage (diagonal runs 50-75 feet) - Speed: Dance sequences, quick entrances/exits - Lighting: Complex, rapidly changing (100+ lighting cues) - Duration: 2-3 hours with intermission

Audience Viewing: - Orchestra: 500-800 seats (ground level) - Mezzanine: 200-400 seats (1 level up) - Balcony: 200-400 seats (2 levels up) - Total: 1,000-1,500 seats typical

### Festival Scale

Outdoor Main Stage: - Width: 60-100 feet (18-30 meters) - Depth: 40-60 feet (12-18 meters) - Height: 30-50 feet (9-15 meters) to truss - Audience area: 50-200 feet deep, 100-200 feet wide - Capacity: 5,000-50,000+ people

Environmental Challenges: - Variable lighting (daylight → sunset → night) - Weather (wind, rain, heat) - Ambient noise - Crowd dynamics - No controlled environment

### Comparison to Current Volumetric Studios

| Venue | Capture Volume | Cameras | Status | Comparable To |
| --- | --- | --- | --- | --- |
| Intel Studios (closed 2020) | 10,000 sq ft | 100+ (8K) | ❌ Closed | Small festival stage |
| Metastage (LA/Vancouver) | ~2,000 sq ft | 100+ (12MP) | ✅ Active | Broadway stage center |
| 4DViews HOLOSYS+ | ~1,500 sq ft | Variable | ✅ Active | Solo/small group |
| Microsoft MRCS | ~500 sq ft dome | 106 (RGB+depth) | ⚠️ Tech licensed | Close-up performance |
| Broadway Stage (target) | ~3,000-6,000 sq ft | 200-400 needed | 🎯 Your goal | Full theatrical production |
| Festival Main Stage | 6,000-12,000 sq ft | 300-600 needed | 🎯 Your goal | Large-scale concert/festival |

Key Insight: You’re targeting 2-10× larger volume than existing professional volumetric studios.

## Broadway Theater Requirements

### Technical Requirements

#### Camera Coverage

Full-Stage Volumetric (Gaussian Splatting):

Camera Count: 200-400 cameras - Stage perimeter: 120-180 cameras (every 1-2 feet around proscenium) - Overhead grid: 40-80 cameras (looking down at stage) - House positions: 40-60 cameras (audience POV, multiple elevations) - Wings/backstage: 20-40 cameras (for full 360° coverage) - Upstage: 20-40 cameras (back wall, cyc coverage)

Camera Specifications: - Resolution: 4K minimum (8K preferred for faces at distance) - Frame rate: 60 fps (dance/action), 120 fps (ideal) - Sync: Hardware genlock (<1ms accuracy across all cameras) - Sensor: Global shutter (no rolling shutter artifacts) - Lenses: 50-85mm equivalent (tight framing on stage from perimeter)

Recommended Hardware: - Option 1 - Machine Vision Cameras (Best): - FLIR Blackfly S 4K: $2,000 each × 300 = $600,000 - Precise genlock, excellent low-light - M12 mount lenses: $200 each × 300 = $60,000

- Option 2 - Cinema Cameras (Highest Quality):

  - Sony A7S III class: $3,500 each × 300 = $1,050,000

  - Best image quality, low-light performance

  - Lenses: $500 each × 300 = $150,000

- Option 3 - Hybrid (Realistic):

  - 100 machine vision (key areas): $200,000

  - 200 GoPro Hero 12 (wide coverage): $80,000

  - Total cameras: $280,000

#### Synchronization System

Requirements: - 300-400 cameras synchronized to <1ms - Genlock distribution across theater - Timecode for post-sync verification

System: - Master clock: GPS-disciplined genlock generator ($5,000-10,000) - Genlock distribution: Fiber optic or SDI splitters ($20,000-40,000) - Backup sync: Timecode generators (Tentacle Sync × 300 = $60,000)

Alternative: Software sync + LED flash sync (less reliable)

Total Sync Hardware: $50,000-100,000

#### Data Capture & Storage

Data Rates: - Per camera: 4K60 @ 100 Mbps (H.265) = 12.5 MB/s - 300 cameras: 3,750 MB/s = 3.75 GB/s sustained - Per minute: 225 GB - Per hour: 13.5 TB - Full show (2.5 hours): 34 TB

Storage Solution:

Option 1 - Distributed (Recommended): - 30 recording stations (10 cameras each) - Each: 2TB NVMe SSD, 10-port capture card - Cost per station: $5,000 - Total: 30 × $5,000 = $150,000

Option 2 - Centralized: - Massive RAID array - 100 Gbps network switches - Total: $200,000-300,000

Working Storage (post-production): - 100 TB NAS: $15,000-30,000 - Backup drives: $10,000

#### Processing Infrastructure

Gaussian Splatting Training: - Input: 300 cameras × 2.5 hours = 750 camera-hours of footage - Training time: 4-8 hours per 1-minute sequence (optimized) - Full show: 150 minutes × 6 hours = 900 GPU-hours

Processing Farm Requirements:

Option 1 - On-Premises: - 10× RTX 4090 workstations: $15,000 each = $150,000 - Process full show in ~4 days (parallelized)

Option 2 - Cloud (AWS, Google, Azure): - 20× A100 instances: $5/hour each - 900 hours ÷ 20 = 45 hours - Cost per show: 45 × 20 × $5 = $4,500 - Annual (52 shows): $234,000

Recommendation: On-premises if >15 shows/year, cloud otherwise

#### Lighting Considerations

Challenge: Theatrical lighting constantly changes - Spotlights on performers - Blackouts, color washes - Strobe effects - Backlighting, silhouettes

Solutions:

- IR Illumination (if production allows):

  - Infrared LED arrays (invisible to audience)

  - Cameras with IR sensitivity

  - Provides constant geometry capture regardless of stage lighting

  - Cost: $20,000-50,000

- High Dynamic Range Capture:

  - Cameras with >13 stops dynamic range

  - Capture highlights (spotlights) and shadows simultaneously

  - Sony A7S III, Canon C70 class

  - Higher cost but handles theatrical lighting

- Multi-Exposure Fusion (research):

  - Alternate cameras at different exposures

  - Fuse in post for full dynamic range

  - Complex but proven in visual effects

Recommended: Option 2 (HDR cameras) + careful placement

### Rig Deployment in Broadway Theater

#### Permanent Installation vs. Portable

Permanent Installation (Ideal): - Cameras mounted to theater structure - Hidden in house (ceiling, box seats, proscenium) - Cabling built into theater - One-time setup, minimal per-show effort - Requires: Long-term venue partnership

Portable Deployment (Realistic): - Cameras on tripods, light stands, truss - Setup: 2-3 days - Strike: 1 day - Repeatable across multiple theaters - Requires: Modular design, trained crew

#### Camera Positions

Example: Typical Broadway Theater (1,200 seats)

Side View:

[PROSCENIUM]
      |
   [STAGE] (50' deep)
      |
━━━━━━━━━━━━━━━━━ ← [Cameras: Front perimeter, 40 cameras, 1.5' spacing]
      ↓
[Orchestra Seating] (500 seats)
   [Cameras: Scattered in house, 20 cameras on tripods, ~6' high]

━━━━━━━━━━━━━━━━━ ← Mezzanine level (4m above orchestra)
[Mezzanine Seating] (300 seats)
   [Cameras: Mezzanine rail, 15 cameras]

━━━━━━━━━━━━━━━━━ ← Balcony level (8m above orchestra)
[Balcony Seating] (400 seats)
   [Cameras: Balcony rail, 10 cameras]


Top-Down View:

        [BACK WALL]
            |
    [CAMERAS: Upstage, 20 cameras]
            |
     ╔═════════════════╗
     ║                 ║ ← Stage (50' × 50')
     ║   [STAGE]       ║
     ║                 ║
     ╚═════════════════╝
            |
[CAMERAS: Proscenium arc, 60 cameras, 180° semicircle]
            ↓
    [Orchestra Seating]
[CAMERAS: House scattered, 20 cameras in aisles/rear]
            ↓
     [Mezzanine/Balcony]
[CAMERAS: Upper levels, 25 cameras total]


Overhead Grid:

     [GRID - 40' above stage]
        ┌─────┬─────┬─────┬─────┐
        │ CAM │ CAM │ CAM │ CAM │
        ├─────┼─────┼─────┼─────┤  ← 40-60 cameras
        │ CAM │ CAM │ CAM │ CAM │     looking down
        ├─────┼─────┼─────┼─────┤     5-8' spacing
        │ CAM │ CAM │ CAM │ CAM │
        └─────┴─────┴─────┴─────┘

Camera Distribution (300-camera system): - Proscenium perimeter: 60 cameras (front/sides of stage) - Overhead grid: 50 cameras (looking down) - Upstage/back wall: 20 cameras (rear coverage) - Stage wings: 30 cameras (15 per side, backstage) - Orchestra level: 40 cameras (audience POV, multiple positions) - Mezzanine level: 30 cameras (elevated audience POV) - Balcony level: 20 cameras (high audience POV) - Stage floor/understage: 20 cameras (upward-looking, for aerial work) - Specialty positions: 30 cameras (follow spots, box seats, etc.)

Total: 300 cameras

#### Minimal Audience Impact

Stealth Deployment:

- Hidden Cameras:

  - Disguised as theatrical equipment (follow spots, monitors)

  - Matte black finish (invisible in dark theater)

  - Silent operation (no cooling fans audible)

- Strategic Placement:

  - Behind proscenium arch (built into structure)

  - In technical positions (lighting catwalks, grid)

  - Dead zones (behind pillars, in projection booth)

  - Aisles (on thin tripods, below sightlines)

- Lighting Integration:

  - Cameras mounted to lighting truss

  - Use existing theater infrastructure

  - Minimal additional rigging

Impact Assessment: - Obstructed seats: 0-10 (premium orchestra, if any) - Visual intrusion: Minimal (cameras blend into technical equipment) - Noise: Silent (fanless cameras or acoustic dampening)

## Festival Requirements

### Festival Stage Challenges

Environmental: - Lighting: Daylight (100,000 lux) → sunset → night (stage lights only) - Weather: Rain, wind, dust - Temperature: Variable (affects equipment) - Vibration: Bass from sound system, crowd movement

Technical Solutions:

- Auto-Exposure Cameras:

  - Handle daylight → nighttime transition

  - Sony A7S III (15+ stops dynamic range)

- Weather Protection:

  - Camera rain covers (Aquatech, Outex)

  - IP65-rated housings for critical positions

  - Cost: $200-500 per camera × 300 = $60,000-150,000

- Stabilization:

  - Rigid truss mounts (no tripods in crowd)

  - Vibration dampening mounts

  - Image stabilization in post

### Festival Deployment Strategy

Stage Coverage (similar to Broadway): - Front-of-stage truss: 80 cameras (arc around stage) - Overhead truss: 60 cameras (looking down at performers) - Side stages/wings: 40 cameras (20 per side) - Upstage/video wall: 20 cameras

Audience Coverage (unique to festivals): - FOH tower (sound booth): 30 cameras (professional mixer perspective) - Crowd platforms: 40 cameras (on scaffolding, 6-12’ high) - Aerial: 20 cameras (on cherry pickers, drones - if permitted) - VIP areas: 10 cameras (side stage, backstage)

Total: 300 cameras minimum (main stage only)

Multiple Stages: - Many festivals have 3-5+ stages - Full coverage: 300 cameras × 3 stages = 900 cameras (prohibitive) - Realistic: Main stage full volumetric (300 cameras), secondary stages traditional 360° stereo (8 cameras each)

### Rigging & Infrastructure

Truss Requirements: - Heavy-duty aluminum truss (12” or 20.5” box truss) - Load capacity: 300 cameras + mounts + cables ≈ 500-800 kg - Truss rental: $5,000-15,000 per event - Rigging crew: 4-8 people × 2 days setup + 1 day strike

Power Distribution: - 300 cameras × 20W = 6,000W continuous - Plus: Recording stations, networking (total ~10 kW) - Generator or venue power (200A service)

Network Infrastructure: - Fiber optic backbone (10-100 Gbps) - Switches at each camera cluster - Central recording/processing hub - Cost: $20,000-50,000 (rental or purchase)

## Full Premium Approach

### System Overview

Concept: Metastage/Intel Studios-class volumetric capture, scaled to Broadway/festival

Components: 1. 300-400 camera multi-view array 2. Hardware genlock synchronization 3. Distributed recording infrastructure 4. GPU processing farm (on-prem or cloud) 5. Gaussian Splatting training pipeline 6. GSVC compression for distribution

Target Output: - Resolution: 8K stereo per eye (volumetric detail) - Frame rate: 60 fps (120 fps for action) - 6DOF range: Full stage (50’ × 50’ × 30’ volume) - Quality: Cinema-grade (indistinguishable from real performance)

### Capital Expenditure

Hardware (Purchased):

| Item | Quantity | Unit Cost | Total |
| --- | --- | --- | --- |
| Machine vision cameras (4K) | 100 | $2,000 | $200,000 |
| GoPro Hero 12 (wide coverage) | 200 | $400 | $80,000 |
| Lenses (machine vision) | 100 | $200 | $20,000 |
| Camera mounts/housing | 300 | $150 | $45,000 |
| Weather protection (festivals) | 300 | $300 | $90,000 |
| Genlock sync system | 1 | $80,000 | $80,000 |
| Recording stations | 30 | $5,000 | $150,000 |
| Network infrastructure | 1 | $50,000 | $50,000 |
| Working storage (100TB NAS) | 1 | $25,000 | $25,000 |
| Processing workstations (10× RTX 4090) | 10 | $15,000 | $150,000 |
| Rigging/truss (owned) | 1 set | $75,000 | $75,000 |
| Cables, adapters, misc | - | - | $50,000 |
| Backup equipment (20%) | - | - | $200,000 |
|  |  | TOTAL | $1,215,000 |

Software: - Gaussian Splatting training software: Nerfstudio (free), custom pipeline development ($50,000-100,000) - Compression (GSVC): Open-source or licensed ($10,000-50,000) - VR player/viewer: Custom development ($50,000-150,000)

Total Software: $110,000-300,000

Grand Total (Full Premium): $1,325,000-1,515,000

### Operational Costs (Per Show)

| Item | Cost |
| --- | --- |
| Crew (setup/strike/operation) | $15,000-25,000 |
| Venue rigging crew | $5,000-10,000 |
| Truss/equipment rental (if not owned) | $10,000-20,000 |
| Power/utilities | $1,000-3,000 |
| Storage media (40TB drives) | $2,000-4,000 |
| Cloud processing (if used) | $4,500-10,000 |
| Insurance | $2,000-5,000 |
| Contingency (10%) | $3,950-7,700 |
|  | TOTAL PER SHOW |
|  | $43,450-84,700 |

Annual Operating Costs (12 shows/year): $521,400-1,016,400

### Amortization

Capital + Year 1 Operating: - Capital: $1,400,000 (midpoint) - Operating: $768,900 (midpoint, 12 shows) - Year 1 Total: $2,168,900

Cost per show (amortized over 3 years): - Capital amortization: $1,400,000 ÷ 36 shows = $38,889/show - Operating: $64,075/show - Total: $102,964 per show

Cost per show (amortized over 5 years): - Capital amortization: $1,400,000 ÷ 60 shows = $23,333/show - Operating: $64,075/show - Total: $87,408 per show

### Advantages

✅ Highest Quality: Cinema-grade volumetric capture ✅ Full 6DOF: Walk anywhere on stage in VR ✅ Facial Detail: 4K-8K cameras capture expressions from distance ✅ Temporal Consistency: 300-400 views = robust Gaussian Splatting ✅ Professional Credibility: Comparable to major VFX studios ✅ Archival Value: Permanent digital preservation of performances ✅ Scalability: System works for Broadway → festivals → stadiums

### Disadvantages

❌ Massive Capital: $1.4M+ upfront ❌ Complex Operations: Requires expert crew (6-12 people) ❌ Long Setup: 2-3 days per venue ❌ Processing Time: Days to weeks per show (900 GPU-hours) ❌ Venue Approvals: Theater/festival management may resist intrusion ❌ Logistics: Transport 300 cameras + infrastructure

## Hybrid Approach (Recommended)

### Concept

Zone-Based Volumetric Capture: - Premium zones: Full Gaussian Splatting (key moments) - Standard zones: Enhanced 360° stereo + depth (general coverage) - Backup zones: Traditional 360° stereo (context)

Rationale: - 80% of viewing time focuses on 20% of stage area (center stage, solos) - Full-stage volumetric is overkill for ensemble scenes (viewers focus on individuals) - Hybrid delivers premium quality where it matters, efficiency elsewhere

### System Design

#### Zone 1: Premium Volumetric (Center Stage)

Coverage: 20’ × 20’ × 20’ volume (center stage, solo performance area)

Hardware: - 80 cameras in dense array around center stage - 40 perimeter (1’ spacing in semicircle) - 20 overhead (grid) - 10 upstage - 10 house (audience POV) - Machine vision cameras (4K60): 80 × $2,000 = $160,000 - Genlock sync (for this zone): $25,000

Output: Premium Gaussian Splatting (cinema-quality)

#### Zone 2: Enhanced Coverage (Full Stage)

Coverage: Entire stage (50’ × 50’) outside Zone 1

Hardware: - 20× 360° stereo rigs (8 cameras each) + depth cameras - Positioned in grid across stage - Each rig: $5,000 + $1,000 depth camera = $6,000 - Total: 20 × $6,000 = $120,000 - Cameras: 20 × 8 = 160 cameras

Output: 360° stereo with limited 6DOF (±1 meter head movement)

#### Zone 3: Audience POV (Multiple Viewpoints)

Coverage: 5-7 audience perspectives (orchestra, mezzanine, balcony, sides)

Hardware: - 6× 360° stereo rigs (8 cameras each) - Orchestra center, front left/right, mezzanine, balcony - Each: $5,000 - Total: 6 × $5,000 = $30,000 - Cameras: 6 × 8 = 48 cameras

Output: Traditional 360° stereo (3DOF, wide compatibility)

### Total Hybrid System

Cameras: - Zone 1 (premium): 80 cameras - Zone 2 (enhanced): 160 cameras - Zone 3 (audience): 48 cameras - Total: 288 cameras

Cost Breakdown:

| Component | Cost |
| --- | --- |
| Zone 1 cameras (premium) | $160,000 |
| Zone 1 sync/infrastructure | $25,000 |
| Zone 2 rigs (20× enhanced 360) | $120,000 |
| Zone 3 rigs (6× standard 360) | $30,000 |
| Central sync system | $30,000 |
| Recording infrastructure | $100,000 |
| Processing workstations (5× RTX 4090) | $75,000 |
| Storage (50TB NAS) | $15,000 |
| Rigging/mounts | $40,000 |
| Cables/misc | $30,000 |
| Weather protection (festivals) | $40,000 |
| Contingency (15%) | $95,000 |
|  | TOTAL |
|  | $760,000 |

Software: $75,000-150,000 (custom viewer with zone switching)

Grand Total (Hybrid): $835,000-910,000

### Operational Workflow

Capture: 1. All 288 cameras rolling simultaneously 2. Premium zone (80 cameras) → Gaussian Splatting training 3. Enhanced zones (20 rigs) → Stereo + depth stitching 4. Audience zones (6 rigs) → Standard 360° stitching

Processing: - Premium zone: 4-8 hours GPU time per minute (parallelized) - Enhanced zones: Real-time or near-real-time stitching - Audience zones: Real-time stitching

Distribution: - Single VR app with intelligent zone switching - User starts in audience view (Zone 3) - Hotspot to “teleport to stage” → Zone 2 (enhanced stereo) - Hotspot to “experience solo up close” → Zone 1 (premium volumetric)

User Experience: - Seamless transitions (fade between zones) - Best quality where viewer attention is focused - Efficient file sizes (premium only for key moments)

### Cost per Show (Hybrid)

Operational: - Crew: $12,000-18,000 - Rigging: $4,000-8,000 - Processing: $2,000-5,000 (partial cloud) - Storage: $1,500-3,000 - Insurance: $1,500-3,000 - Misc: $2,000-4,000 - Total: $23,000-41,000 per show

Amortized (3 years, 36 shows): - Capital: $875,000 ÷ 36 = $24,306/show - Operating: $32,000/show (midpoint) - Total: $56,306 per show

Amortized (5 years, 60 shows): - Capital: $875,000 ÷ 60 = $14,583/show - Operating: $32,000/show - Total: $46,583 per show

### Advantages

✅ Lower Capital: $875K vs. $1.4M (38% savings) ✅ Faster Setup: Fewer cameras, modular zones ✅ Flexible: Scale zones up/down per production ✅ Premium Quality: Where it matters (solos, key moments) ✅ Efficient Processing: Only premium zone requires heavy GPU ✅ Better ROI: Lower cost, comparable viewer experience ✅ Realistic Crew: 4-6 people (vs. 8-12 for full premium)

### Trade-offs

⚠️ Limited Full Volumetric: Only 20’×20’ premium zone ⚠️ Zone Switching: Viewer transitions between quality levels ⚠️ Choreography Dependent: Need to know where performers will be for premium zone placement

## Emerging Technology Path

### Wait-and-See Strategy

Rationale: Technology improving rapidly (2025-2027)

Expected Breakthroughs:

- Single/Few-Camera Volumetric (2026-2027):

  - AI-based depth estimation from RGB video

  - 1-4 cameras → volumetric output

  - Example: NeRF from sparse views (DropGaussian, InstantMesh evolution)

  - Impact: Eliminate 300-camera rigs, use 10-20 high-quality cameras

- Real-Time Gaussian Splatting (2026):

  - Capture → instant Gaussian Splat (no training)

  - Instant Gaussian Stream (CVPR 2025) maturing

  - Impact: Same-day turnaround (vs. days/weeks processing)

- AI-Generated Volumetric Enhancement (2026-2027):

  - 360° stereo capture → AI upscales to volumetric

  - Fill in missing views using generative models

  - Impact: Use existing 360° rigs, AI adds volumetric quality

- Professional Spatial Video Ecosystem (2025-2026):

  - Canon EOS VR system evolution

  - APMP standard adoption

  - Impact: Off-the-shelf Broadway spatial video (not quite 6DOF, but close)

### Interim Strategy (2025-2026)

Phase 1: Today (November 2025) - Deploy hybrid 360° stereo + depth (Zone 2 approach) - 20-30 rigs across Broadway stage - Cost: $120,000-180,000 - Output: 2.5D (limited 6DOF, ±1 meter)

Phase 2: Mid-2026 - Add premium volumetric zone (Zone 1) when technology matures - AI-assisted volumetric from fewer cameras (40-80 vs. 300-400) - Cost: Additional $150,000-250,000 - Output: Full 6DOF for key zones

Phase 3: 2027+ - Replace multi-camera with AI-based volumetric - 10-20 high-quality cameras (Sony A7S III class) - AI fills in volumetric detail - Cost: $70,000-140,000 (cameras only) - Output: Full-stage volumetric from sparse capture

Advantage: Lower upfront investment, ride technology curve

Disadvantage: Delayed premium volumetric, may miss market window

## Operational Considerations

### Broadway Theater Partnerships

Key Requirements:

- Production Rights:

  - Actors’ Equity approval (performer rights)

  - Producers’ permission (show rights)

  - Venue approval (theater management)

  - Licensing agreements (music, choreography)

- Technical Integration:

  - Load-in windows (limited time for setup)

  - Union crew requirements (IATSE)

  - Fire marshal approval (safety, emergency exits)

  - Minimal impact on production (no show delays)

- Revenue Share:

  - Typical split: 50-70% to producers, 30-50% to capture team

  - Minimum guarantee vs. percentage

  - Ancillary rights (streaming, VR distribution)

Example Deal Structure: - Upfront: $50,000-100,000 per show (covers operational costs) - Revenue share: 30% of VR ticket sales - Rights: 5-year exclusive VR distribution - Deliverables: VR experience ready within 3 months

### Festival Partnerships

Differences from Broadway: - Shorter setup window: Often 1 day or less - Outdoor challenges: Weather, power, security - Multiple stages: Need to prioritize (main stage vs. secondary) - Artist approvals: Varies by performer contract

Partnership Model: - Festival as client: Pays for capture service - Festival as partner: Revenue share from VR ticket sales - Sponsor model: Brand sponsors volumetric capture (e.g., “Presented by Meta”)

Example: Coachella VR - Capture main stage headliners (3-5 performances) - Festival provides power, rigging access, crew - Split VR streaming revenue 50/50 - Sponsor (e.g., T-Mobile) covers capture costs

### Crew Requirements

Full Premium (300-400 cameras): - Technical Director: 1 - Camera Engineers: 4-6 (camera setup, alignment) - Network Engineers: 2 (sync, recording infrastructure) - Rigging Specialists: 2-4 (venue-provided or hired) - Data Wranglers: 2-3 (backup, storage management) - On-Set Supervisor: 1 (live monitoring) - Total: 12-18 people

Hybrid (288 cameras): - Technical Director: 1 - Camera Engineers: 3-4 - Network Engineer: 1 - Rigging Specialists: 2 - Data Wranglers: 2 - On-Set Supervisor: 1 - Total: 10-12 people

Setup Timeline: - Day 1: Rigging, major infrastructure (4-8 people) - Day 2: Camera mounting, cabling (6-10 people) - Day 3: Alignment, calibration, testing (full crew) - Show day: Minimal (2-3 people monitoring) - Strike: 1 day (6-8 people)

Labor Costs (per show, including setup/strike): - Union crew (Broadway): $800-1,200/day per person - Non-union (festivals): $400-700/day per person - Total: $15,000-25,000 per show

### Venue Limitations

Broadway Theaters: - ✅ Controlled environment (lighting, climate) - ✅ Power available (200A service typical) - ✅ Rigging infrastructure (catwalks, grid) - ❌ Limited load-in (usually 1 day or less) - ❌ Union requirements (IATSE crew mandatory) - ❌ Historic buildings (cannot modify structure)

Festivals: - ✅ Large setup windows (days before festival) - ✅ Flexible rigging (build custom truss) - ❌ Weather exposure (rain, wind, dust) - ❌ Power challenges (generators, distribution) - ❌ Security (equipment theft risk)

## Case Studies & Precedents

### Intel Studios (2018-2020) - Closed

System: - 10,000 sq ft capture volume - 100+ 8K cameras - Real-time volumetric processing (proprietary)

Productions: - Volumetric films (Venice Film Festival 2020) - Sports content (NBA, NFL) - Music performances

Closure Reason: High operational costs, limited ROI

Lesson: Scale matters - Broadway/festival capture needs sustainable business model

### Metastage (2018-Present) - Active

System: - ~2,000 sq ft capture volume - 100+ 12MP machine vision cameras - Microsoft MRCS technology

Productions: - Music videos (volumetric performances) - VR experiences (live-action holograms) - Commercials, film VFX

Business Model: - Per-session fees ($10,000-50,000) - Revenue share on distribution - Sustainable at smaller scale

Relevance: Proven that volumetric capture is commercially viable with right partnerships

### Broadway HD / BroadwayDirect (2D Streaming)

System: - Multi-camera 2D video capture - Professional broadcast equipment - ~8-12 cameras per show

Distribution: - Streaming platform (subscription + PPV) - Licensing to theaters (NT Live model)

Revenue: - $500,000-2M per show (estimates) - Split with producers (typically 50/50)

Relevance: Existing market for Broadway capture, VR is premium tier

Opportunity: Volumetric capture = differentiated product (not competing with 2D streams)

### Meta Horizon Hyperscape (2024-Present) - Consumer

System: - Mobile phone capture (photogrammetry) - Cloud Gaussian Splatting processing - Quest 3 streaming

Scale: Small rooms/spaces (not Broadway-sized)

Lesson: Consumer expects easy capture. Professional volumetric needs to deliver premium quality to justify complexity.

## Detailed Cost Analysis

### Full Premium vs. Hybrid - 5-Year Comparison

Assumptions: - 12 shows per year (Broadway: 8 shows, Festivals: 4 shows) - 5-year equipment lifespan - VR ticket sales: $20/viewer, 5,000 viewers per show average

| Metric | Full Premium | Hybrid |
| --- | --- | --- |
| Initial Investment | $1,400,000 | $875,000 |
| Operating Cost (per show) | $64,075 | $32,000 |
| Operating Cost (annual, 12 shows) | $768,900 | $384,000 |
| 5-Year Total Cost | $5,244,500 | $2,795,000 |
| Cost per show (5-year avg) | $87,408 | $46,583 |
| Revenue per show (5K viewers × $20) | $100,000 | $100,000 |
| Annual Revenue (12 shows) | $1,200,000 | $1,200,000 |
| 5-Year Total Revenue | $6,000,000 | $6,000,000 |
| 5-Year Profit | $755,500 | $3,205,000 |
| ROI | 54% | 365% |
| Break-even | Year 2.5 | Year 1.5 |

Conclusion: Hybrid approach is 4× more profitable while delivering comparable quality

### Sensitivity Analysis

If viewer demand exceeds estimates:

| Viewers per Show | Annual Revenue | Full Premium Profit (5yr) | Hybrid Profit (5yr) |
| --- | --- | --- | --- |
| 5,000 (base) | $1,200,000 | $755,500 | $3,205,000 |
| 10,000 | $2,400,000 | $6,755,500 | $9,205,000 |
| 20,000 | $4,800,000 | $18,755,500 | $21,205,000 |
| 50,000 | $12,000,000 | $54,755,500 | $57,205,000 |

At scale (50K viewers), both approaches highly profitable. Hybrid still has $2.5M edge due to lower costs.

## 3-Year Roadmap

### Year 1 (2026): Foundation

Q1 (Jan-Mar 2026): - ✅ Finalize system design (hybrid vs. full premium) - ✅ Secure initial funding ($875K-1.4M) - ✅ Build relationships with 2-3 Broadway producers - ✅ Partner with 1-2 festivals (Coachella, Bonnaroo, etc.)

Q2 (Apr-Jun 2026): - ✅ Order camera equipment (6-month lead time for 300 cameras) - ✅ Hire core team (TD, engineers) - ✅ Develop custom Gaussian Splatting pipeline - ✅ Build processing infrastructure (workstations or cloud setup)

Q3 (Jul-Sep 2026): - ✅ Equipment arrives, assemble rigs - ✅ Test deployment (small theater or rehearsal space) - ✅ Calibration, software testing - ✅ First festival capture (late summer festival)

Q4 (Oct-Dec 2026): - ✅ First Broadway show capture (off-Broadway or preview) - ✅ Iterate based on learnings - ✅ Develop VR viewer app (Unity/Unreal) - ✅ Soft launch (friends/family, beta testers)

Year 1 Metrics: - Shows captured: 2-4 - Revenue: $200,000-400,000 (early adopters, test pricing) - Lessons learned: Technical workflow, venue partnerships

### Year 2 (2027): Scale

Q1 (Jan-Mar 2027): - ✅ Public launch (VR app on Quest Store, Vision Pro App Store) - ✅ Capture 3-4 Broadway shows (full season) - ✅ Marketing campaign (PR, influencers, theater community)

Q2 (Apr-Jun 2027): - ✅ Expand festival coverage (4-6 festivals) - ✅ Introduce subscription model ($15/month for library access) - ✅ Optimize processing pipeline (reduce turnaround time)

Q3 (Jul-Sep 2027): - ✅ International expansion (West End London capture) - ✅ Licensing deals (theaters, streaming platforms) - ✅ Upgrade to emerging tech (AI-assisted volumetric if mature)

Q4 (Oct-Dec 2027): - ✅ Holiday season push (capture Nutcracker, holiday shows) - ✅ Corporate partnerships (Meta, Apple co-marketing) - ✅ Year-end review, plan for Year 3 expansion

Year 2 Metrics: - Shows captured: 12-16 - Revenue: $1,200,000-2,000,000 - Subscribers: 5,000-10,000 (library access) - Break-even: Achieved (hybrid approach)

### Year 3 (2028): Dominance

Objectives: - Industry leader in volumetric live events - 30+ shows per year - International presence (US, UK, Europe, Asia) - Technology licensing (sell system to other capture teams)

Revenue Streams: 1. Per-show VR tickets: $100,000-500,000 per show 2. Subscription service: 20,000 subscribers × $180/year = $3,600,000 3. Licensing to theaters: $500,000-1,000,000 4. Technology licensing: $1,000,000+ (sell system to competitors) 5. Sponsorships: $500,000-2,000,000 (brands sponsor captures)

Year 3 Revenue: $6,000,000-10,000,000

Year 3 Profit: $3,000,000-6,000,000 (50-60% margin at scale)

## ROI & Business Model

### Revenue Streams

#### 1. VR Ticket Sales (Primary)

Model: Pay-per-view for each show - Price: $15-30 per show (vs. $100-300 Broadway ticket) - Target: VR headset owners who can’t attend live - Audience: - International (can’t travel to Broadway) - Budget-conscious (cheaper than live ticket) - Accessibility (wheelchair users, hearing impaired with captions) - Nostalgia (see show again after live attendance)

Conversion: - Broadway show: 300,000-500,000 potential viewers (theater fans globally) - Conservative: 1% conversion = 3,000-5,000 viewers - Optimistic: 5% conversion = 15,000-25,000 viewers

Revenue per Show: - Conservative: 5,000 viewers × $20 = $100,000 - Optimistic: 20,000 viewers × $25 = $500,000

#### 2. Subscription Service

Model: Netflix-style library access - Price: $15-20/month - Content: Library of 10-50+ shows (grows over time) - Target: Dedicated theater/VR enthusiasts

Projections: - Year 1: 1,000-2,000 subscribers = $180,000-480,000/year - Year 2: 5,000-10,000 subscribers = $900,000-2,400,000/year - Year 3: 20,000-50,000 subscribers = $3,600,000-12,000,000/year

Churn: 5-10%/month (typical for entertainment subscriptions)

#### 3. Licensing to Theaters

Model: License VR experience to performing arts centers, museums - Price: $5,000-20,000 per venue per year - Use case: Show VR experience in theater lobby, museums

Projections: - Year 1: 5-10 venues = $25,000-200,000 - Year 2: 20-50 venues = $100,000-1,000,000 - Year 3: 100+ venues = $500,000-2,000,000

#### 4. Technology Licensing

Model: Sell/license capture system to other production companies - Price: $100,000-500,000 per system + 5-10% royalty on their revenue - Target: Regional theaters, international markets, competitors

Projections: - Year 2: 1-2 licenses = $100,000-1,000,000 - Year 3: 5-10 licenses = $500,000-5,000,000 + ongoing royalties

#### 5. Sponsorships & Brand Partnerships

Model: Corporate sponsors fund captures - Example: “Hamilton VR - Presented by Meta Quest” - Price: $100,000-500,000 per show (sponsor pays capture costs) - Benefit: Sponsor gets branding, may distribute to customers

Projections: - Year 2: 2-4 sponsored shows = $200,000-2,000,000 - Year 3: 10-20 sponsored shows = $1,000,000-10,000,000

### Total Revenue Potential (Year 3)

| Revenue Stream | Conservative | Optimistic |
| --- | --- | --- |
| VR Ticket Sales (30 shows) | $3,000,000 | $15,000,000 |
| Subscriptions (20-50K subs) | $3,600,000 | $12,000,000 |
| Theater Licensing (100 venues) | $500,000 | $2,000,000 |
| Technology Licensing (5-10 systems) | $500,000 | $5,000,000 |
| Sponsorships (10-20 shows) | $1,000,000 | $10,000,000 |
|  | TOTAL |  |
|  | $8,600,000 | $44,000,000 |

Realistic (midpoint): $20,000,000-25,000,000 in Year 3

### Investment Ask

Seed Round (Year 0-1): $2,000,000 - Equipment: $875,000 (hybrid system) - Software development: $150,000 - Working capital (crew, ops): $500,000 - Marketing/business development: $300,000 - Contingency: $175,000

Use of Funds: - Capture 4-6 shows in Year 1 (prove model) - Build technology and team - Establish partnerships (Broadway producers, festivals)

Valuation: $8,000,000 pre-money (25% equity for $2M)

Exit Strategy: - Acquisition by Meta, Apple, or entertainment company (Year 3-5) - Exit valuation: $50M-150M (based on $20M+ revenue, high growth) - Investor return: 6-18× in 3-5 years

## Technical Implementation Guide

### Phase 1: System Design (Months 1-3)

Tasks: 1. Finalize camera count and positions (300-400 vs. 288 hybrid) 2. Select camera models (machine vision vs. cinema vs. GoPro mix) 3. Design sync system (genlock vs. timecode) 4. Choose processing approach (on-prem vs. cloud) 5. Software architecture (Gaussian Splatting pipeline)

Deliverables: - Detailed system spec document - CAD models of camera positions - Data flow diagrams - Budget breakdown - Risk assessment

### Phase 2: Procurement (Months 4-6)

Tasks: 1. Order cameras (lead time: 8-12 weeks for 300 units) 2. Order sync equipment 3. Build/order recording stations 4. Purchase/build workstations 5. Develop rigging designs

Challenges: - Bulk discounts (negotiate with manufacturers) - Supply chain (backup vendors) - Import/customs (if buying internationally)

### Phase 3: Assembly & Testing (Months 7-9)

Tasks: 1. Assemble camera rigs 2. Build recording infrastructure 3. Set up processing workstations 4. Develop calibration procedures 5. Test in controlled environment (warehouse, rehearsal space)

Deliverables: - Fully assembled system - Calibration procedures - Setup/strike checklists - Crew training materials

### Phase 4: Pilot Deployment (Month 10-12)

Tasks: 1. Deploy at small venue (off-Broadway, small festival) 2. Capture 1-2 test shows 3. Process and generate Gaussian Splats 4. Build VR viewer (Unity/Unreal) 5. Beta test with 50-100 users

Success Metrics: - Setup time <3 days - Capture success (>95% cameras working) - Processing time <1 week per show - User satisfaction >4.0/5.0

### Phase 5: Production Launch (Year 2+)

Tasks: 1. Capture 12-30 shows per year 2. Iterate on workflow 3. Optimize processing (reduce turnaround) 4. Expand distribution (more platforms) 5. Scale team and equipment

## Conclusion

### Recommended Path: Hybrid Approach

Why Hybrid: 1. Capital Efficient: $875K vs. $1.4M (38% savings) 2. Proven ROI: 365% over 5 years vs. 54% for full premium 3. Faster Break-Even: 1.5 years vs. 2.5 years 4. Flexibility: Easier to scale up/down per production 5. Quality Where It Matters: Premium volumetric for solos, efficient coverage elsewhere

When to Upgrade to Full Premium: - Revenue exceeds $5M/year (can afford $1.4M reinvestment) - Demand for full-stage volumetric confirmed - Technology improves (AI reduces camera count)

### Next Steps (November 2025 → Launch)

Immediate (Next 3 Months): 1. ✅ Secure initial funding ($875K-2M) 2. ✅ Build relationships with 3-5 Broadway producers 3. ✅ Visit 2-3 festivals to assess feasibility 4. ✅ Assemble advisory board (Broadway insiders, VR experts, investors)

Q1 2026: 1. ✅ Finalize system design (hybrid recommended) 2. ✅ Order equipment (cameras, sync, processing) 3. ✅ Hire core team (Technical Director, 2-3 engineers)

Q2-Q3 2026: 1. ✅ Build and test system 2. ✅ Pilot capture (1-2 shows) 3. ✅ Develop VR viewer app

Q4 2026: 1. ✅ Public launch 2. ✅ Scale to 12+ shows/year

By 2028: - Industry leader in volumetric live events - $20M+ annual revenue - Proven, profitable business model

### The Opportunity

Broadway + Festivals volumetric capture is a greenfield market with: - ✅ Proven demand (BroadwayHD, NT Live show 2D market exists) - ✅ Technology ready (Gaussian Splatting production-ready November 2025) - ✅ Hardware capable (Vision Pro M5, Quest 3) - ✅ Limited competition (no one doing Broadway volumetric at scale) - ✅ High margins (50-60% profit at scale)

Window of opportunity: 2026-2028 (before competitors enter market)

Your advantage: Early mover, deep understanding of technology, relationships with venues/producers

## Resources & Further Reading

### Technical References

- Gaussian Splatting: https://repo-sam.inria.fr/fungraph/3d-gaussian-splatting/

- GSVC Compression: ACM NOSSDAV 2025 proceedings

- Instant Gaussian Stream: CVPR 2025 proceedings

- Nerfstudio: https://docs.nerf.studio/

### Industry Examples

- Metastage: https://metastage.com/

- 4DViews: https://www.4dviews.com/

- Broadway HD: https://www.broadwayhd.com/

### Business Models

- National Theatre Live: https://www.ntlive.com/ (2D cinema model)

- Met Opera Live in HD: (2D cinema model, $20M+ revenue)

### VR Distribution

- Meta Quest Store: https://www.meta.com/experiences/

- Apple Vision Pro App Store: visionOS apps

- SteamVR: PC VR distribution

Document Version: 1.0 Date: November 15, 2025 Author: Broadway & Festival Volumetric Strategy Team Status: Strategic Planning Document Next Update: Post-pilot capture (Q4 2026)